|  |  |
| --- | --- |
| **ALMOST, MAINE** **Rehearsal Report # 1** **Date: Tuesday, October 6, 2020**  | **Director:** Tyler Harrison**Stage Manager:** Lauren Daniels**Location:** WilsonBlack Box Theater |

|  |  |
| --- | --- |
| **REHEARSAL SCHEDULE (*what is scheduled)*:** **Start:** 4:00PM-4:45PM, Blocking Scene 1 & 2**Break**: 4:45PM-5:00PM**Start:** 5:00PM-5:45PM, Blocking Scene 3 & 4**Break:** 5:45PM-6:00PM**Start:** 6:00PM-6:45PM, Walk thru Scenes 1-4**Notes:** 6:45PM**End:** 7PM | **REHEARSAL BREAKDOWN *(what actually happens)*:** **Start:** 4:00PM-4:50PM, Blocking Scene 1 & 2**Break**: 4:50PM-5:05PM**Start:** 5:00PM-5:40PM, Blocking Scene 3 **Break:** 5:40PM-6:00PM, Company business**Start:** 6:00PM-6:45PM, Walk thru Scenes 1-3**Notes:** 6:50PM**End:** 7:10PM**Run Time:** Scenes 1-3: 53 Minutes |
| Present: | Director, Assistant Director, Stage Manager, Assistant Stage Manager 1, Assistant Stage Manager 2, Costumer, Actor 1, Actor 2, Actor 3, Actor 4, Actor 5, Actor 6 |
| Absent/Late:  | Actor 5 – Late, prearranged |

|  |
| --- |
| **General Notes:** Accidents/Injuries – NoneThanks to all who attended the first blocking rehearsal!  |
| **Stage Management:** Reschedule Friday’s rehearsal to run until 7:30 PM, send a note to cast and crew |
| **Sets:**What will be in the wings during the transition from Scene 1 to Scene 2? Can we get 6 actors off quickly? |
| **Costumes:**Actors 1, 3, and 4 were measured during company business.  |
| **Sound:**Need a car door slamming Scene 2 |
| **Lights:**Nothing to report |
| **Properties:**Need a bunch of daisies for Actor 2 in Scene 3.  |
| **Publicity/Front of House:** Need to schedule a photoshoot for the flyer and program cover.  |
| **Next Production Meeting (Schedule & Notes to discuss):** Discuss tech week rehearsal schedule Follow up on Scene 1-2 Transition  |