|  |  |
| --- | --- |
| **ALMOST, MAINE**  **Rehearsal Report # 1**  **Date: Tuesday, October 6, 2020** | **Director:** Tyler Harrison  **Stage Manager:** Lauren Daniels  **Location:** WilsonBlack Box Theater |

|  |  |  |
| --- | --- | --- |
| **REHEARSAL SCHEDULE (*what is scheduled)*:**  **Start:** 4:00PM-4:45PM, Blocking Scene 1 & 2  **Break**: 4:45PM-5:00PM  **Start:** 5:00PM-5:45PM, Blocking Scene 3 & 4  **Break:** 5:45PM-6:00PM  **Start:** 6:00PM-6:45PM, Walk thru Scenes 1-4  **Notes:** 6:45PM  **End:** 7PM | | **REHEARSAL BREAKDOWN *(what actually happens)*:**  **Start:** 4:00PM-4:50PM, Blocking Scene 1 & 2  **Break**: 4:50PM-5:05PM  **Start:** 5:00PM-5:40PM, Blocking Scene 3  **Break:** 5:40PM-6:00PM, Company business  **Start:** 6:00PM-6:45PM, Walk thru Scenes 1-3  **Notes:** 6:50PM  **End:** 7:10PM  **Run Time:** Scenes 1-3: 53 Minutes |
| Present: | Director, Assistant Director, Stage Manager, Assistant Stage Manager 1, Assistant Stage Manager 2, Costumer, Actor 1, Actor 2, Actor 3, Actor 4, Actor 5, Actor 6 | |
| Absent/Late: | Actor 5 – Late, prearranged | |

|  |
| --- |
| **General Notes:**  Accidents/Injuries – None  Thanks to all who attended the first blocking rehearsal! |
| **Stage Management:**  Reschedule Friday’s rehearsal to run until 7:30 PM, send a note to cast and crew |
| **Sets:**  What will be in the wings during the transition from Scene 1 to Scene 2? Can we get 6 actors off quickly? |
| **Costumes:**  Actors 1, 3, and 4 were measured during company business. |
| **Sound:**  Need a car door slamming Scene 2 |
| **Lights:**  Nothing to report |
| **Properties:**  Need a bunch of daisies for Actor 2 in Scene 3. |
| **Publicity/Front of House:**  Need to schedule a photoshoot for the flyer and program cover. |
| **Next Production Meeting (Schedule & Notes to discuss):**  Discuss tech week rehearsal schedule  Follow up on Scene 1-2 Transition |